**3.1 Project Timeline with Benchmarks**

**April:**

-Create survey form and interview outline with guiding questions

-purchase incentives for participants

-coordinate with other parties regarding venue/days to set up at venue (school, gym, etc. to speak with people and hand out surveys)

-Select locations for one-on-one interviews (in two cities- Kamloops and Williams Lake)

-Hand out surveys in selected areas/ ask likely businesses or workplaces for permission to hand

out surveys and conduct brief interviews.

-Beginning of data collection via surveys and interviews

**May:**

-Review current data collected

-Request more surveys to be filled or more interviews if more information needed; check for

experimenter errors

-Once interviews and all surveys completed, prize draw if people not compensated individually

**June:**

-Final analysis of all data.

-identify recurring patterns of themes in data

-compare results to preexisting literature

**July:**

-Synthesis of information from both surveys and interviews.

-Typed report of results, limitations discovered while conducting research

-Submit report to selected professional periodicals/ BCCASW for consideration/publishing